## Slide 1: Migration Approach – Schneider Electric
Mani Manavalan
05/21/2019

## Slide 2: Execution approach
Migration Strategy
Model
Approach
Staggered Model
Scope defined in terms of “Wave and Iteration". Each Iteration undergoes a Release Lifecycle of Migration, Testing and Deployment (Production Roll-out) Phases
Approach by Product APIs, High Impact and Redesigning
Planned migration approach with waves and iterations based on refactor/redesign, high impact, product API and
Outcomes
Standard redefined/refactored APIs delivered.
Product and high impact APIs prioritized for delivery.
Leverage automated tools and reusable components.
Lower risk in terms of execution.
Learnings & Best Practices in terms of process optimization from previous iteration will be incorporated on continued basis
Teams will have early view of overall migration process and provide feedback
WSO2 APIs
Reverse Engineer
Analysis and Planning
Prioritize and Grouping
Eliminate un-used APIs
Refactor/Redefine + Build
Validation
Go Live
Phased /Iterative
Migration
Pre Migration
Migration High Level Approach

## Slide 3: WSO2 APIM to APIGEE Migration Steps
Phase 1
Phase 2
Backend System
Developer Apps
1. Consumers traffic routed to APIGEE server. DNS Routing enabled in SE’s network
2. APIGEE will redirect the traffic to WSO2 APIM. Firewall opening and IP whitelisting executed by SE’s network team.
Goal:
All API traffic through APIGEE Server
One pilot API tested in QA.
Developer Apps
Backend System
3. Development : migration executed in waves and iterations.
4. Minimal Consumer Impact: Configured amount of traffic in APIGEE environment after migration.
1
2
Pass-through Migration
API Migration
Goal
WSO2 legacy APIs Migration complete
Disconnect WSO2 APIM from live API traffic
APIs ready for SE certification
API Product Strategy
Consumer Based: One product for each consumer in phase 2
Capability Based: API product capability based products decided later.
API Redefined/Refactored
Oauth Token transferred
Points to backend system
APIGEE or APIM
% Traffic
% Traffic
% Traffic
Migration not completed - 100%
3
4
Migration not completed - 100%

## Slide 4: Prioritize APIs - Waves and Iteration
Pilot: Count 1 - BFO-MyCase:v1.0
Iteration 1 - Count 10 - CKM and SOAP-GSE APIs
Iteration 2 - Count 09 - CKM and SOAP-GSE APIs
Iteration 3 - Count 22 – SPJ, FIO, MYSE and SR APIs, Zillant APIs
Iteration 4 - Count 22 - BFO, BOX , EBILL, EUT, GSE, PRM, SR APIs
Iteration 5 - Count 13 – BFS, BOX, CMS EAA, ERP and TalentLink APIs
Iteration 6 - Count 9 - ACME, Q2C, EUT, SAPCN and User APIs
Iteration 7 - Count 9 - BEM, ETAX, IFW, OneTool and User APIs
Iteration 1 - Count 15 – BFO APIs without BFO access token validation
Iteration 2 - Count 14 – BFO APIs without BFO access token validation
Iteration 3 - Count 18 - BFO APIs with BFO access token validation
Iteration 4 - Count 18 - BFO APIs with BFO access token validation
Iteration 5 - Count 27 - EBILL APIs (including SOAP APIs)
Iteration 6 - Count 20 – AMS, BDO, BFS, Blackline, and ERP APIs
Iteration 7 - Count 20 - GSE, MYSE, Installed Base and Newton APIs
Iteration 8 - Count 16 - SAP, ERP, FIO, OnleClick, OneTool, Telescope APIs
Iteration 1 - Count 5 – AR APIs
Iteration 2 - Count 6 – CPQ and SAP PI Backend APIs
Iteration 3 - Count 14 - Go-Digital and SDH
Iteration 4 - Count 15 – PIM APIs
Iteration 5 - Count 5 - IDMS APIs
Migrate Product API candidates
High Impact API
Business Critical & Redesign Refactoring APIs
Wave 1 - Migration Goal
Product API candidates and High Impact APIs
Business Critical APIs
Redesign Refactoring APIs
Wave 2 - Migration Goal
Wave 3 - Migration Goal
Business Critical APIs
20+ APIs under development in APIM
**Zero transaction APIs will not be migrated across all waves
Phase 2

## Slide 5: Execution Plan
Blackout Period
PHASE | May -2019 | June-2019 | July-2019 | Aug-2019 | Sep-2019 | Oct-2019 | Nov-2019 | Dec-2019
WSO2 APIM Assessment
Assessment Complete
APIGEE Passthrough proxy + 1 API Testing signoff complete.
Migration Plan Approved
Phase 1 Execution + Pilot
Wave 1 Completion
Wave 2 Completion
Wave 3 Completion
Sunset WSO2 APIM
Approved
113 PD, 94 APIs migrated
580 PD, 145 APIs migrated
378 PD, 45 APIs migrated
2 Resources
Phase 1
Phase 2
Functional testing complete in QA environment
Performance test execution is not in scope. Migration team involve only for support
APIs are ready to promoted to pre-prod and prod environment
2 Resources
Final version of Migration approach completed
APIM high level assessment completed.
Detailed level assessment will be carried out in each iteration.
Decision to sunset WSO2 APIM in place
Zero transaction APIs – ~13%.
APIs under development in APIM – 20 - 25
9 to 10 Resources

## Slide 6: Estimation & Resource Loading
Efforts displayed in hours and total in PD
Wave 1 Efforts in PD | 113
Wave 2 Efforts in PD | 580
Wave 3 Effort in PD | 378
Average Effort per API 3.75 PD
Total Migration Effort 1127 PD
Chart: Resources for Migration
| 43635 | 43665 | 43696 | 43727 | 43757 | 43788 | 43818
Onsite Lead | 1 | 1 | 1 | 1 | 1 | 1 | 1
Offshore Lead | 1 | 1 | 1 | 1 | 1 | 1 | 1
Onsite Sr.Developer | 1 | 1 | 1 | 1 | 1 | 1 | 1
Offshore Sr.Developer | 1 | 1 | 1 | 1 | 1 | 1 | 1
Onsite Developers | 1 | 2 | 2 | 2 | 2 | 2
OffshoreDevelopers | 1 | 2 | 4 | 4 | 4 | 2
 | Activity | Simple | Medium | Complex
Reverse Engineering | Document APIM logic | 2 | 5 | 8
 | APIM logic KT |  |  | 
Design | Design Migration components in APIGEE | 0 | 3 | 5
 | IFW Orchestration design to APIGEE |  |  | 
 | Reusable Artifact Mapping Analysis |  |  | 
Development | Pass-through | 4 | 14 | 24
 | Header & Token Mapping |  |  | 
 | Payload Mapping |  |  | 
 | Routing & Mash up |  |  | 
 | Scripts(JS/Node) |  |  | 
 | Security |  |  | 
 | Loggigng |  |  | 
 | Fault Handling |  |  | 
 | Threat Protection |  |  | 
 | Proxy Chaining / Aggregation |  |  | 
Testing | Unit Test | 3 | 11 | 16
 | Integration Test |  |  | 
 | Functional Test |  |  | 
 | Performance Test |  |  | 
Other Activities | Consumer Communications | 2 | 3 | 4
 | APP and Product Creation |  |  | 
 | Key/Secret Migration for Products |  |  | 
 | Publish API to Portal |  |  | 
 | Total in PD | 1.375 | 4.5 | 7.125
 | Agverage effort per API |  |  | 
 | After10% effort reduced using APIMakr tool | 1.2375 | 4.05 | 6.4125