## 3
sl.no | API_Name_Version | Test cases received | TestCase Dump Date | Refined Test cases Delivered | Refined TestCase Delivery Date | Assignee | Comment
1 | BFO-Attachment:v1.0 | 3 | Yes |  |  | Thejas
2 | EUT-GetVATDetails:v1.0 | 3 | Yes |  |  | Thejas
3 | PRM-Cockpit:v1.0 | 3 | Yes |  |  | Thejas
4 | PRM-Invoice:v1.0 | 3 | Yes |  |  | Thejas
5 | PRM-Notification:v1.0 | 3 |  |  |  |  | Decommission
6 | PRM-Notification:v1.1 | 3 | Yes |  |  | Thejas
7 | SOAP-EUT-GetVATDetails:v1.0 | 3 | Yes |  |  | Thejas
8 | SOAP-GSE-EntitlementOrder:v1.0 | 3 | Yes |  |  | Thejas
9 | SOAP-GSE-EntitlementOrder:v1.1 | 3 | Yes |  |  | Thejas
10 | SOAP-GSE-ProductPackagingService:v1.0 | 3 | Yes |  |  | Thejas
11 | SOAP-GSE-UserOrgHierarchy:v1.0 | 3 | Yes |  |  | Thejas
12 | PRM-PartnerLocator:v1.0 | 3 | Yes |  |  | Thejas
13 | SOAP-GSE-ManageDevice:v1.0 | 3 | Yes |  |  | Thejas
14 | SOAP-GSE-UserOrgHierarchy:v2.0 | 3 | Yes |  |  | Thejas
15 | SOAP-LicenseService:v1.0 | 3 | Yes |  |  | Thejas
| Total APIs Identified | 15
| Total Test Cases Executed | 14
| Total API Decommissioned | 1
| Total APIs in APIgee | 14
| Pending Test Case | 0
| Total API Duplicate | 0

## 4.1
sl.no | API_Name_Version | Test cases recevied | Refined Test cases Delivered | Assignee | TestCase Dump Delivery Date | Refined TestCase Delivery Date | Comment
1 | AMS-Case:v1.0 | yes | Yes | Mohit | 2019-06-26 | 2019-06-27
2 | BDO-Repository:v2.0 | yes | Yes | Chandru | 2019-06-26 | 2019-06-27
4 | BEM-SEAdvProposal:v1.0 | yes | Yes | Mohit | 2019-06-26 | 2019-06-27
5 | BFS-PartsOrder:v1.0 | Yes | Yes | Thejas | 2019-06-26 | 2019-07-01 | Present in 6 as well
6 | BFS-ServiceContract:v1.0 | yes | Yes | Mohit | 2019-06-25 | 2019-06-26 | Present in 6 as well
7 | Blackline-JournalEntry:v1.0 | yes | yes | Mohit | 2019-06-25 | 2019-06-26
8 | BOX-Collaboration:v1.0 | yes | Yes | Thejas | 2019-06-26 | 2019-06-27 | Decommission
9 | BOX-File:v1.0 | yes | yes | Mohit | 2019-06-25 | 2019-06-26 | Decommission
10 | BOX-Folder:v1.0 | yes | Yes | Chandru | 2019-06-27 | 2019-06-28 | Decommission
11 | BOX-Search:v1.0 | yes | Yes | Thejas | 2019-06-27 | 2019-07-01 | Decommission
12 | BOX-Token:v1.0 | yes | Yes | Thejas | 2019-06-27 | 2019-06-27 | Decommission
13 | CMS-CreditRequest:v1.0 | yes | yes | Mohit | 2019-06-27 | 2019-06-26
14 | CPQ-Quote:v1.0 | yes | Yes | Chandru | 2019-06-26 | 2019-06-28
15 | Distributor-SPJ-Rebate:v1.0 | yes | Yes | Chandru | 2019-06-26 | 2019-07-01
16 | EAA-Case:v1.0 | yes | yes | Mohit | 2019-06-27 | 2019-06-28
17 | EBILL-AccountingPeriod:v1.0 | Yes | Yes | Thejas | 2019-06-25 | 2019-06-25
18 | EBILL-Authentication:v1.0 | Yes | Yes | Chandru | 2019-06-25 | 2019-07-01
19 | EBILL-BFO-AccountProfile:v2.0 | yes | Yes | Thejas | 2019-06-25 | 2019-06-26
20 | EBILL-Contact:v1.0 | yes | Yes | Thejas | 2019-06-26 | 2019-06-26
21 | EBILL-Invoice:v2.0 | Yes | Yes | Thejas | 2019-06-26 | 2019-06-26
22 | EBILL-PaymentMethod:v1.1 | yes | yes | Chandru | 2019-06-25 | 2019-06-27
23 | EBILL-Staging:v1.0 | Yes | Yes | Thejas | 2019-06-25 | 2019-06-25
24 | EBILL-UpdateAccount:v1.0 | yes | Yes | Thejas | 2019-06-25 | 2019-06-28
25 | EBILL-Usage:v1.0 | Yes | Yes | Thejas | 2019-06-26 | 2019-07-02
26 | Edicom-Invoice:v1.0 | Yes | yes | Chandru | 2019-06-26 | 2019-07-02
28 | ERP-CostCenter:v1.1 | Yes | Yes | Mohit | 2019-06-26 | 2019-06-26
29 | ERP-Employee:v1.0 | yes | Yes | Mohit | 2019-06-26 | 2019-06-27
30 | ERP-InternalOrder:v1.0 | Yes | Yes | Chandru | 2019-06-26 | 2019-07-01
31 | ERP-PostFinanceDocument:v1.0 | Yes | yes | Thejas | 2019-06-26 | 2019-06-30
32 | ERP-Price:v1.0 | yes | Yes | Mohit | 2019-06-26 | 2019-06-27
33 | ERP-ProjectOrder:v1.0 | yes | Yes | Chandru | 2019-06-25 | 2019-06-28
34 | ERP-PSProject:v1.0 | yes | Yes | Thejas | 2019-06-25 | 2019-07-01
35 | ERP-SalesOrder:v3.1 | Yes | Yes | Chandru | 2019-06-25 | 2019-07-02
36 | ERP-SalesOrder:v4.0 | Yes | Yes | Chandru | 2019-06-25 | 2019-07-02
37 | ERP-SalesOrderBOM:v1.0 | Yes | yes | Chandru | 2019-06-25 | 2019-06-30
38 | ERP-SalesOrderBOM:v2.0 | Yes | Yes | Chandru | 2019-06-25 | 2019-07-02
39 | ERP-ServiceOrder:v1.0 | Yes | Yes | Chandru | 2019-06-26 | 2019-06-28
40 | ERP-WBS:v1.0 | yes | Yes | Thejas | 2019-06-26 | 2019-06-27
41 | GSE-EntitlementLineItem:v2.0 | yes | Yes | Mohit | 2019-06-26 | 2019-06-28 | Present in 4.2 as well
43 | IFW-JobManagement:v1.0 | Yes | Yes | Chandru | 2019-06-26 | 2019-07-01
44 | IFW-ReferenceIds:v1.0 | Yes | yes | Mohit | 2019-06-26 | 2019-07-01
45 | InstalledBase:v3.1 | yes | Yes | Chandru | 2019-06-26 | 2019-06-28
46 | InstalledBase:v4.0 | yes | yes | Thejas | 2019-06-26 | 2019-06-30
47 | Oracle-SOAP-ERP-SalesOrderServiceContract:v1.0 | Yes | Yes | Thejas | 2019-06-26 | 2019-07-02
50 | SAP-Job:v1.0 | Yes | Yes | Thejas | 2019-06-26 | 2019-07-01
52 | SOAP-EBILL-GetSubscriptionDetails:v1.0 | Yes | Yes | Thejas | 2019-06-26 | 2019-07-02
53 | Zilliant-Counter:v1.0 | Yes | Yes | Thejas | 2019-06-26 | 2019-07-02 | Decommission
54 | Zilliant-Deal:v1.0 | Yes | Yes | Thejas | 2019-06-26 | 2019-07-01 | Decommission
55 | Email:v1.0 | Yes | Yes | Chandru | 2019-06-26 | 2019-07-02
57 | Distributor-SPJ-Rebate:v1.1 | Yes | yes | Mohit | 2019-06-26 | 2019-07-01
58 | SEACat-Asset:v1.0 | Yes | Yes | Thejas | 2019-06-26 | 2019-07-01
| Total APIs Identified | 51
| Total Test Cases Executed | 51
| Total API Decommissioned | 7
| Total APIs in APIgee | 44
| Pending Test Case | 0
| Total API Duplicate | 0

## 4.2
sl.no | API_Name_Version | Test cases recevied | TestCase Dump Date | Refined Test cases Delivered | Refined TestCase Delivery Date | Assignee | Comment
1 | InstalledBase:v3.0 | Yes | 2019-07-02 | Yes | 2019-07-03 | Thejas
2 | MES-Product:v1.0 | Yes | 2019-07-02 | Yes | 2019-07-03 | Chandru
3 | MYSE-Order:v2.0 | Yes | 2019-07-02 | Yes | 2019-07-03 | Thejas
4 | MYSE-PriceAndAvailability:v2.1 | Yes | 2019-07-02 | yes | 2019-07-05 | Chandru
5 | MYSE-TempAccountAccess:v1.0 | yes | 2019-07-10 | Yes | 2019-07-11 | Thejas
6 | MYSE-User:v1.0 | Yes | 2019-07-04 | yes | 2019-07-05 | Chandru
7 | Product-Availability:v1.0 | Yes | 2019-07-10 | Yes | 2019-07-11 | Thejas
8 | Product-StockLevelChecker:v1.0 | Yes | 2019-07-02 | Yes | 2019-07-03 | Chandru
9 | SOAP-ERP-GetSalesOrderPrice:v2.0 | Yes | 2019-07-02 | Yes | 2019-07-04 | Thejas
10 | SOAP-ERP-UpdatePlannedCostsAndRevenues:v1.0 | Yes | 2019-07-02 | Yes | 2019-07-03 | Chandru
11 | SOAP-ETAX-CalculateTax:v1.0 | Yes | 2019-07-02 | yes | 2019-07-04 | Thejas
12 | SOAP-IFW-CustomerFeedAcknowledgement:v1.0 | Yes | 2019-07-04 | yes | 2019-07-04 | Chandru
13 | SOAP-ITDERP-CreditApplication:v1.0 | Yes | 2019-07-02 | yes | 2019-07-04 | Thejas
14 | SOAP-OneClick-CreateSalesOrderBOM:v1.0 | Yes | 2019-07-02 | Yes | 2019-07-08 | Chandru
15 | SOAP-OneClick-MaintainSalesOrder:v1.0 | Yes | 2019-07-02 | Yes | 2019-07-09 | Thejas
16 | SOAP-OneClick-Satelite-UpdatePSProject:v1.0 | Yes | 2019-07-02 | Yes | 2019-07-08 | Chandru
17 | SR-BOM:v1.0 | Yes | 2019-07-02 | Yes | 2019-07-08 | Thejas
18 | SXON-Case:v1.0 | Yes | 2019-07-02 | Yes | 2019-07-09 | Chandru
19 | TalentLink-BulkEmployee:v2.0 | Yes | 2019-07-02 | Yes | 2019-07-05 | Thejas
20 | TalentLink-Employee:v2.0 | Yes | 2019-07-02 | Yes | 2019-07-03 | Chandru
21 | Telescope-Asset:v1.0 | Yes | 2019-07-02 |  |  | Thejas | Decommission
22 | UIMS-User:v2.0 | Yes | 2019-07-02 | Yes | 2019-07-03 | Chandru
23 | SEACat-User:v1.0 | Yes | 2019-07-02 | Yes | 2019-07-10 | Thejas
24 | BDO-Repository:v1.0 | yes | 2019-07-03 | yes | 2019-07-04 | Chandru
25 | ERP-CostCenter:v1.0 | Yes | 2019-07-10 | Yes | 2019-07-10 | Thejas
26 | PRM-Profile:v1.0 | Yes | 2019-07-03 | Yes | 2019-07-03 | Thejas
27 | PRM-Registration:v1.0 | Yes | 2019-07-03 | Yes | 2019-07-03 | Thejas
28 | CKM-FAQ:v1.0 | Yes | 2019-07-09 | Yes | 2019-07-09 | Thejas
29 | CKM-Private-FAQ:v1.0 | Yes | 2019-07-09 | Yes | 2019-07-09 | Thejas
30 | ERP-HoldSource:v1.0 | Yes | 2019-07-04 | Yes | 2019-07-04 | Chandru
31 | ERP-Stock:v1.0 | Yes | 2019-07-04 | Yes | 2019-07-04 | Chandru
32 | SOAP-ERP-CreateSalesOrder:v1.0 | Yes | 2019-07-04 | yes | 2019-07-10 | Thejas
33 | SOAP-ERP-GetMaterialInventoryDetails:v1.0 | Yes | 2019-07-04 | Yes | 2019-07-10 | Thejas
34 | SOAP-FIO-FulfillPayments:v1.0 | Yes | 2019-07-04 | Yes | 2019-07-11 | Chandru
35 | SOAP-FIO-FulfillProvisioning:v1.0 | Yes | 2019-07-04 | Yes | 2019-07-12 | Chandru
36 | SOAP-GSE-CreateDeviceEntitlement:v1.0 | Yes | 2019-07-04 | Yes | 2019-07-05 | Chandru | Present in 8 as well
37 | SOAP-OneTool-Ticket:v1.0 | Yes | 2019-07-04 | Yes | 2019-07-04 | Chandru
38 | SOAP-OneTool-TicketOutbound:v1.0 | Yes | 2019-07-04 | Yes | 2019-07-08 | Chandru
39 | GSE-EntitlementLineItem:v2.0 | Yes | 2019-07-04 | Yes | 2019-07-05 | Chandru | Present in 4.1 as well
| Total APIs Identified | 39
| Total Test Cases Executed | 37
| Total API Decommissioned | 1
| Total API Duplicate | 1
| Total APIs in APIgee | 37
| Pending Test Case | 0

## 5
sl.no | API_Name_Version | Test cases received | TestCase Dump Date | Refined Test cases Delivered | Refined TestCase Delivery Date | Assignee
1 | ACME-GetAddressDetails:v1.0 | Yes | 2019-07-08 |  |  |  | 1) The functionality in GoDigital(the only consumer subscribed this API) where this API is called is disabled as confirmed by GoDigital team (Stephane Tellier)
2 | AR-Asset:v1.0 | Yes | 2019-07-08 | Yes | 2019-07-11 | Thejas
3 | AR-Authentication:v1.0 | Yes | 2019-07-08 | Yes | 2019-07-09 | Chandru
4 | AR-Catalog:v1.0 | Yes | 2019-07-08 | Yes | 2019-07-10 | Chandru
5 | AR-Registration:v1.0 | Yes | 2019-07-08 | Yes | 2019-07-11 | Chandru
6 | AR-Site:v1.0 | Yes | 2019-07-08 | Yes | 2019-07-10 | Chandru
7 | DFSERP-DOMFinanceDocument:v1.0 | Yes | 2019-07-08 | Yes | 2019-07-09 | Chandru
8 | EBILL-CheckProductEligibility:v1.0 | Yes | 2019-07-08 | Yes | 2019-07-12 | Thejas
9 | ERP-Client:v1.0 | Yes | 2019-07-08 | Yes | 2019-07-10 | Chandru
10 | ERP-InboundDelivery:v1.0 | Yes | 2019-07-11 | Yes | 2019-07-12 | Thejas
11 | ERP-PurchaseOrder:v1.0 | Yes | 2019-07-11 | Yes | 2019-07-12 | Thejas
12 | ERP-TransferOrder:v1.0 | Yes | 2019-07-08 | Yes | 2019-07-10 | Chandru
13 | FIO-FulfillPayments:v1.0 | Yes | 2019-07-08 | Yes | 2019-07-11 | chandru
14 | FIO-FulfillProvisioning:v2.0 | Yes | 2019-07-08 | yes | 2019-07-11 | chandru
15 | GoDigital-User:v1.0 | Yes | 2019-07-09 |  |  | Thejas | Present in sprint 8
16 | GSE-User:v1.0 | Yes | 2019-07-08 |  |  |  | Decommission
17 | MYSE-OrderSummary:v1.0 | Yes | 2019-07-08 | Yes | 2019-07-12 | chandru
18 | MySE-ProductAvailability:v2.1 | Yes | 2019-07-08 | Yes | 2019-07-12 | chandru
19 | Q2C-Feature:v1.0 | Yes | 2019-07-09 | Yes | 2019-07-11 | Chandru
20 | Q2C-Quote:v1.0 | Yes | 2019-07-09 | Yes | 2019-07-11 | Chandru
21 | Q2C-SPJRebate:v1.0 | Yes | 2019-07-09 | Yes | 2019-07-12 | chandru
22 | SAPERP-JournalEntry:v1.0 | Yes | 2019-07-08 | Yes | 2019-07-15 | chandru
23 | SOAP-SAPCN-ATPCheck:v1.0 | Yes | 2019-07-10 | Yes | 2019-07-15 | chandru
24 | SOAP-SAPCN-OGStockCheck:v1.0 | Yes | 2019-07-10 | yes | 2019-07-12 | Thejas
25 | SR-Auth:v1.0 | Yes | 2019-07-08 | Yes | 2019-07-16 | Thejas
26 | SR-Bookmark:v1.0 | Yes | 2019-07-08 |  |  |  | moved to sprint 10
27 | SR-Community:v1.0 | Yes | 2019-07-08 | Yes | 2019-07-16 | Thejas
28 | SR-Document:v1.0 | Yes | 2019-07-08 | Yes | 2019-07-17 | Thejas
29 | SR-Preference:v1.0 | Yes | 2019-07-08 |  |  |  | moved to sprint 10
30 | SR-Product:v1.1 | Yes | 2019-07-08 | Yes | 2019-07-16 | Chandru
31 | SR-Repository:v1.2 | Yes | 2019-07-08 | Yes | 2019-07-12 | Chandru
32 | SR-SharedCommunity:v1.1 | Yes | 2019-07-08 | Yes | 2019-07-16 | Chandru
33 | SR-Switchboard:v1.1 | Yes | 2019-07-08 | Yes | 2019-07-15 | Chandru
34 | SR-User:v1.0 | Yes | 2019-07-08 |  |  |  | moved to sprint 10
35 | UIMS-User:v1.0 | No test cases | NA | NA | NA |  | Decommission
36 | ANC-Quote:v1.0 | Yes | 2019-07-08 | Yes | 2019-07-09 | Chandru
37 | BDO-Currency:v1.0 | Yes | 2019-07-08 | Yes | 2019-07-09 | Chandru
| Total APIs Identified | 34* | * 3 APIs were moved to sprint10
| Total Test Cases Executed | 30
| Total API Decommissioned | 2
| Total APIs in APIgee | 32
| Pending Test Case | 2
| Total API Duplicate | 0

## 6
sl.no | API_Name_Version | Test cases received | TestCase Dump Date | Refined Test cases Delivered | Refined TestCase Delivery Date | Assignee | Comment
1 | BFO-AccountAttribute:v1.0 | Yes | 2019-07-15 | Yes | 2019-05-16 | Chandru
2 | BFO-AccountRelatedList:v1.1 | Yes | 2019-07-15 | Yes | 2019-07-19 | Thejas
3 | BFO-Approval:v1.1 | Yes | 2019-07-15 | Yes | 2019-07-24 | Chandru
4 | BFO-Case:v2.1 | Yes | 2019-07-15 | Yes | 2019-07-23 | Thejas
5 | BFO-Competitor:v1.0 | Yes | 2019-07-15 | Yes | 2019-07-17 | Chandru
6 | BFO-ContactRelatedList:v1.0 | Yes | 2019-07-15 | Yes | 2019-07-23 | Thejas
7 | BFO-DependentPicklist:v1.0 | Yes | 2019-07-15 | yes | 2019-07-18 | Chandru
8 | BFO-DiscussionTopic:v1.0 | Yes | 2019-07-15 | Yes | 2019-07-23 | Thejas
9 | BFO-Favourite:v1.0 | Yes | 2019-07-15 | Yes | 2019-07-17 | Chandru
10 | BFO-GetZQuoteAttachmentDetails:v1.0 | Yes | 2019-07-15 | Yes | 2019-07-24 | Thejas
11 | BFO-GlobalSearch:v1.0 | Yes | 2019-07-15 | Yes | 2019-07-17 | Chandru
12 | BFO-InstalledProducts:v1.0 | Yes | 2019-07-15 | Yes | 2019-07-24 | Thejas
13 | BFO-MasterProject:v1.0 | Yes | 2019-07-15 | yes | 2019-07-18 | Chandru
14 | BFO-MyCase:v2.1 | Yes | 2019-07-15 | Yes | 2019-07-25 | Thejas
15 | BFO-Opportunity:v3.3 | Yes | 2019-07-15 | Yes | 2019-07-24 | Chandru
16 | BFO-OpportunityRelatedList:v1.3 (Pick @ Last) | Yes | 2019-07-15 | yes | 2019-08-01 | Thejas
17 | BFO-Product:v1.0 | Yes | 2019-07-15 | Yes | 2019-07-17 | Chandru
18 | BFO-ProductSearch:v1.0 | Yes | 2019-07-15 | Yes | 2019-07-25 | Thejas
19 | BFO-QuoteLink:v1.0 | Yes | 2019-07-15 | yes | 2019-07-19 | Chandru
20 | BFO-SalesEntity:v1.0 | Yes | 2019-07-15 | Yes | 2019-07-25 | Thejas
21 | BFO-Token:v1.0 | Yes | 2019-07-15 | Yes | 2019-08-02 | Chandru
22 | BFO-WorkOrderNotification:v1.0 | Yes | 2019-07-15 | Yes | 2019-07-29 | Thejas
23 | BFO-ZQuote:v1.0 | Yes | 2019-07-16 | yes | 2019-07-18 | Chandru
24 | BFS-PartsOrder:v1.0 | Yes | 2019-07-15 | Yes | 2019-07-29 | Thejas | Present in sprint 4.1
25 | BFS-ServiceContract:v1.0 | Yes | 2019-07-15 | Yes | 2019-07-17 | Chandru | Present in sprint 4.1
26 | SOAP-BFO-GetGateManagers:v1.0 | Yes | 2019-07-18 | Yes | 2019-07-18 | Thejas
27 | SOAP-BFO-RegisterCase:v1.0 | Yes | 2019-07-15 | Yes | 2019-07-17 | Chandru
28 | SOAP-BFO-UpdateOpportunityQuote:v2.0 | Yes | 2019-07-15 | yes | 2019-07-18 | Thejas
29 | BFO-Case:v1.0 | Yes | 2019-07-18 | yes | 2019-07-18 | Chandru
30 | BFO-Case:v1.1 | Yes | 2019-07-18 | Yes | 2019-07-23 | Chandru
31 | BFO-Case:v1.2 | Yes | 2019-07-18 | Yes | 2019-07-23 | Chandru
32 | BFO-CreditRequest:v1.0 | Yes | 2019-07-18 | Yes | 2019-07-19 | Chandru
33 | BFO-GateManagers:v1.0 | Yes | 2019-07-18 | Yes | 2019-07-18 | Thejas
34 | BFO-MyCase:v1.0 | Yes | 2019-07-23 | Yes | 2019-07-29 | Thejas
35 | BFO-MyCase:v2.0 | Yes | 2019-07-18 | Yes | 2019-07-30 | Thejas
36 | BFO-Opportunity:v2.0 | Yes | 2019-07-18 | yes | 2019-07-31 | Thejas
| Total APIs Identified | 36
| Total Test Cases Executed | 36
| Total API Decommissioned | 0
| Total APIs in APIgee | 34
| Pending Test Case | 0
| Total API Duplicate | 2

## 7
sl.no | API_Name_Version | Test cases received | TestCase Dump Date | Refined Test cases Delivered | Refined TestCase Delivery Date | Assignee | Comment
1 | EBILL-Accounting:v1.0 | Yes | 2019-08-06
2 | EBILL-Product:v1.0 | Yes | 2019-07-22
3 | IDMS-Transliteration:v2.0 | Yes | 2019-07-22 | Yes | 2019-08-05 | Thejas
4 | IDMS-User:v3.0 | Yes | 2019-07-22 | Yes | 2019-07-30 |  | Issue in the backend for send invitation
5 | IDMS-User:v4.0 | Yes | 2019-07-22
6 | IDMS-User:v4.1 | Yes | 2019-07-22 | Yes | 2019-08-01 |  | Bug @ IFW Level send invitation
7 | PIM-Document:v1.0 | Yes | 2019-07-25 | Yes | 2019-08-05 | Thejas
8 | PIM-DocumentSecure:v1.0 | Yes | 2019-07-25 |  |  |  | Getting 403 Forbidden from backend
9 | PIM-File:v1.0 | Yes | 2019-07-22 | Yes | 2019-08-07 | Thejas
10 | PIM-IncrementalCategory:v1.0 | Yes | 2019-07-22 | Yes | 2019-08-07 | Thejas
11 | PIM-IncrementalDocument:v1.0 | Yes | 2019-07-22 | Yes | 2019-08-07 | Thejas
12 | PIM-IncrementalProduct:v1.0 | Yes | 2019-07-22
13 | PIM-IncrementalRange:v1.0 | Yes | 2019-07-22
14 | PIM-Product:v1.0 | Yes | 2019-07-22 | Yes | 2019-08-13 | Thejas
15 | PIM-Product:v1.1 | Yes | 2019-07-22 | Yes | 2019-08-21 | Thejas
16 | PIM-Product:v2.0 | Yes | 2019-07-22 | Yes | 2019-08-21 | Thejas
17 | PIM-Product:v2.1 | Yes | 2019-07-22
18 | PIM-ProductOffer:v1.0 | Yes | 2019-07-25 | Yes | 2019-08-19 | Thejas
19 | PIM-Search:v1.0 | Yes | 2019-07-22
20 | PIM-Substitution:v1.0 | Yes | 2019-07-22
21 | SDH-Account:v1.0 | Yes | 2019-07-22 | Yes | 2019-08-06 | Thejas
22 | SDH-Asset:v1.0 | Yes | 2019-07-22 | Yes | 2019-08-07 | Thejas
23 | SDH-CrossRef:v1.0 | Yes | 2019-07-22 | Yes | 2019-08-01 | Chandru
24 | SDH-CrossRef:v2.0 | Yes | 2019-07-22 | Yes | 2019-08-02 | Chandru
25 | SDH-Employee:v1.0 | Yes | 2019-07-22 | Yes | 2019-07-24 | Chandru
26 | SDH-EmployeeBulk:v1.0 | Yes | 2019-07-25 | Yes | 2019-07-29 | Chandru
27 | SDH-Hierarchy:v1.0 | Yes | 2019-07-22 | Yes | 2019-07-24 | Chandru
28 | SDH-Material:v1.0 | Yes | 2019-07-22 | Yes | 2019-07-24 | Chandru
29 | SDH-MultiCurrency:v1.0 | Yes | 2019-07-25 | Yes | 2019-08-05 | Chandru
30 | SDH-Search:v1.0 | Yes | 2019-07-22 | Yes | 2019-07-25
31 | SDH-Search:v2.0 | Yes | 2019-07-22 | Yes | 2019-07-25
32 | SOAP-PIM-Document:v1.0 | Yes | 2019-07-22 | Yes | 2019-08-07 | Thejas
33 | SOAP-SDH-ApplyMultiCurrency:v1.0 | Yes | 2019-07-22 | Yes | 2019-08-07 | Thejas
34 | SOAP-SDH-GetAccount:v1.0 | Yes | 2019-07-22 | Yes | 2019-08-07 | Thejas
35 | SOAP-SDH-GetCrossReference:v1.0 | Yes | 2019-07-22 | Yes | 2019-08-07 | Thejas
| Total APIs Identified | 35
| Total Test Cases Executed | 26
| Total API Decommissioned | 0
| Total APIs in APIgee | 35
| Pending Test Case | 9

## 8
sl.no | API_Name_Version | Test cases received | TestCase Dump Date | Refined Test cases Delivered | Refined TestCase Delivery Date | Assignee | Comment
1 | BFO-User:v1.0 | Yes | 2019-07-24 | Yes | 2019-08-07 | chandru
2 | BFO-User:v1.1 | Yes | 2019-07-24 | Yes | 2019-08-13 | Thejas
3 | BFO-UserAccount:v1.0 | Yes | 2019-07-24
4 | BFO-UserRecordAccess:v1.0 | Yes | 2019-07-24
5 | GoDigital-User:v1.0 | Yes | 2019-07-24 |  |  |  | Present in sprint 5
6 | Newton-FeatureAcknowledgement:v1.0 | Yes | 2019-07-24
7 | Newton-QuoteAcknowledgement:v1.0 | Yes | 2019-07-24
8 | Newton-SalesOrderAcknowledgement:v1.0 | Yes | 2019-07-24
9 | Newton-SalesOrderErrorAcknowledgement:v1.0 | Yes | 2019-07-24
10 | Newton-SalesOrderPriceAcknowledgement:v1.0 | Yes | 2019-07-24
11 | Newton-SPJRebateAcknowledgement:v1.0 | Yes | 2019-07-24
12 | Newton-SPJRebateErrorAcknowledgement:v1.0 | Yes | 2019-07-24
13 | SOAP-GSE-CreateDeviceEntitlement:v1.0 | Yes | 2019-07-24 | Yes | 2019-07-05 | Chandru | Already Delivered as a part of sprint4.2
| Total APIs Identified | 13
| Total Test Cases Executed | 2
| Total API Decommissioned | 0
| Total APIs in APIgee | 11
| Pending Test Case | 9
| Total API Duplicate | 2

## 9
sl.no | API_Name_Version | Test cases received | TestCase Dump Date | Refined Test cases Delivered | Refined TestCase Delivery Date | Assignee | Comment
1 | BFO-Account:v1.4 | Yes | 2019-07-29
2 | BFO-Contact:v2.4 | Yes | 2019-07-29
3 | BFO-Event:v3.0 | Yes | 2019-08-02
4 | BFO-File:v1.0 | Yes | 2019-07-29
5 | BFO-MyCase:v2.2 | Yes | 2019-08-02
6 | BFO-Task:v1.2 | Yes | 2019-07-29
7 | EBILL-Account:v2.3 | Yes | 2019-07-29
8 | EBILL-GSE-Site:v3.0 | Yes | 2019-07-29
9 | EBILL-Staging:v2.0 | Yes | 2019-08-02
10 | EBILL-Subscription:v2.4 | Yes | 2019-07-29
11 | ERP-Price:v2.0 | Yes | 2019-07-29
12 | ERP-TransferOrder:v1.1 | Yes | 2019-07-29
13 | GoDigital-User:v1.1 | Yes | 2019-07-29
14 | GSE-EntitlementLineItem:v3.0 | Yes | 2019-08-02
15 | GSE-FulfillEntitlements:v2.0 | Yes | 2019-08-02
16 | GSE-TransferEntitlementLineItems:v2.0 | Yes | 2019-08-02
17 | GSE-User:v2.0 | Yes | 2019-07-29
18 | MDG-Supplier:v1.0 | Yes | 2019-07-29
19 | MDM-AddressFinder:v1.0 | Yes | 2019-07-29
20 | OneTool-Ticket:v1.0 | Yes | 2019-07-29
21 | ServiceChannel-BFS-WorkOrder:v1.0 | Yes | 2019-08-05
22 | SOAP-BFO-GetCase:v1.0 | Yes | 2019-08-05
23 | SOAP-GSE-EntitlementOrder:v2.0 | Yes | 2019-08-21
24 | SOAP-GSE-ProductPackagingService:v2.0 | Yes | 2019-08-21
25 | SOAP-GSE-UserOrgHierarchy:v3.0 | Yes | 2019-08-21
26 | SSPSRM-Supplier:v1.0 | Yes | 2019-07-29
| Total APIs Identified | 26
| Total Test Cases Executed | 0
| Total API Decommissioned/Duplicate | 0
| Total APIs in APIgee | 26
| Pending Test Case | 26

## 10
sl.no | API_Name_Version | Test cases received | TestCase Dump Date | Refined Test cases Delivered | Refined TestCase Delivery Date | Assignee | Comment
1 | EBILL-Staging:v1.1
2 | SOAP-BFO-UpdateOpportunityQuote:v1.0
3 | SR-Bookmark:v1.0 | [5 empty] | moved from sprint 5 to 10
4 | SR-Preference:v1.0 | [5 empty] | moved from sprint 5 to 10
5 | SR-User:v1.0 | [5 empty] | moved from sprint 5 to 10
6 | TalentLink-BulkEmployee:v1.0
7 | TalentLink-Employee:v1.0
8 | ERP-SalesOrder:v1.0
9 | EBILL-Account:v2.2
10 | BFO-ProjectCategorizationQuestions:v1.0
11 | SOAP-BFO-GetCase:v1.0
| Total APIs Identified | 11
| Total Test Cases Executed | 0
| Total API Decommissioned/Duplicate | 0
| Total APIs in APIgee | 11
| Pending Test Case | 11

## summary
sl.no | Sprint | Total APIs Identified for Migration | Test Case Delivered | Pending
1 | 3 | 14 | 14 | 0
2 | 4.1 | 44 | 44 | 0
3 | 4.2 | 37 | 37 | 0 | Test Cases Submitted | 187
4 | 5.1 | 32 | 30 | 2 | Total Remaining | 57
5 | 6 | 34 | 34 | 0
6 | 7.1 | 35 | 26 | 9
7 | 8 | 11 | 2 | 9
8 | 9 | 26 | 0 | 26
9 | 10 | 11 | 0 | 11
| Total | 244 | 187 | 57

## Consolidated_APIs
sl.no | API_Name(Current) | API_Name(Proposed) | Base Path (Proposed) | Provider | Remarks
1 | ACME-GetAddressDetails:v1.0 | AddressDetails | /v1/{capability}/address-details | ACME
2 | AMS-Case:v1.0 |  |  | AMS
3 | ANC-Quote:v1.0 |  |  | ANC
4 | AR-Asset:v1.0 |  |  | AR
5 | AR-Authentication:v1.0 |  |  | AR
6 | AR-Catalog:v1.0 |  |  | AR
7 | AR-Registration:v1.0 |  |  | AR
8 | AR-Site:v1.0 |  |  | AR
9 | BDO-Currency:v1.0 | CurrencyConversion | /v1/{capability}/currency-conversions | BDO
10 | BDO-Repository:v1.0 | RepositoryLog | /v1/{capability}/repository-logs | BDO
11 | BDO-Repository:v2.0 | RepositoryLog | /v2/{capability}/repository-logs | BDO
12 | BEM-SEAdvProposal:v1.0 | Proposal | /v1/{capability}/proposals | BEM
13 | BFO-Account:v1.4 |  |  | BFO
14 | BFO-AccountAttribute:v1.0 | AccountAttribute | /v1/{capability}/account-attributes | BFO
15 | BFO-AccountRelatedList:v1.1 | AccountRelatedList | /v1.1/{capability}/account-related/list | BFO
16 | BFO-Approval:v1.1 | Approval | /v1.1/{capability}/approvals | BFO
17 | BFO-Attachment:v1.0 |  |  | BFO
18 | BFO-Case:v1.0 |  |  | BFO
19 | BFO-Case:v1.1 |  |  | BFO
20 | BFO-Case:v1.2 |  |  | BFO
21 | BFO-Case:v2.1 |  |  | BFO
22 | BFO-Competitor:v1.0 | Competitor | /v1/{capability}/competitors | BFO
23 | BFO-Contact:v2.4 |  |  | BFO
24 | BFO-ContactRelatedList:v1.0 | Contact Management | /v1/{capability}/contact-management | BFO
25 | BFO-CreditRequest:v1.0 | CreditRequestStatus | /v1/{capability}/credit-request/status | BFO
26 | BFO-DependentPicklist:v1.0 | DependentPicklist | /v1/{capability}/dependent-picklists | BFO
27 | BFO-DiscussionTopic:v1.0 | DiscussionTopic | /v1/{capability}/discussion-topics | BFO
28 | BFO-Event:v3.0 | EventManagement | /v3/{capability}/event-management | BFO
29 | BFO-Favourite:v1.0 | Favourite | /v1/{capability}/favourites | BFO
30 | BFO-File:v1.0 |  |  | BFO
31 | BFO-GateManagers:v1.0 |  |  | BFO
32 | BFO-GetZQuoteAttachmentDetails:v1.0 | ZQuoteAttachment | /v1/{capability}/zquote-attachments | BFO
33 | BFO-GlobalSearch:v1.0 | GlobalSearch | /v1/{capability}/global-search | BFO
34 | BFO-InstalledProducts:v1.0 | InstalledProduct | /v1/{capability}/installedproducts | BFO
35 | BFO-MasterProject:v1.0 | MasterProject | /v1/{capability}/master-projects | BFO
36 | BFO-MyCase:v1.0 | MyCase | /v1/{capability}/my-cases | BFO
37 | BFO-MyCase:v2.0 | MyCase | /v2/{capability}/my-cases | BFO
38 | BFO-MyCase:v2.1 | MyCase | /v2.1/{capability}/my-cases | BFO
39 | BFO-MyCase:v2.2 | MyCase | /v2.2/{capability}/my-cases | BFO
40 | BFO-Opportunity:v2.0 | Opportunity | /v2/{capability}/opportunity | BFO
41 | BFO-Opportunity:v3.3 | Opportunity | /v3.3/{capability}/opportunity | BFO
42 | BFO-OpportunityRelatedList:v1.3 | OpportunityRelatedList | /v3.3/{capability}/opportunity-related-list | BFO
43 | BFO-Product:v1.0 |  |  | BFO
44 | BFO-ProductSearch:v1.0 | ProductSearch | /v1/{capability}/product-search | BFO
45 | BFO-ProjectCategorizationQuestions:v1.0 | ProjectCategorizationQuestions | /v1/{capability}/project-categorization/questions | BFO
46 | BFO-QuoteLink:v1.0 | QuoteLink | /v1/{capability}/quote-links | BFO
47 | BFO-SalesEntity:v1.0 | SalesEntity | /v1/{capability}/quote-links | BFO
48 | BFO-Task:v1.2 | Task | /v1.2/{capability}/sales-entity | BFO
49 | BFO-Token:v1.0 |  |  | BFO
50 | BFO-User:v1.0 |  |  | BFO
51 | BFO-User:v1.1 |  |  | BFO
52 | BFO-UserAccount:v1.0 | UserAccount | /v1/{capability}/user-account | BFO
53 | BFO-UserRecordAccess:v1.0 | UserRecordAccess | /v1/{capability}/user-record/access | BFO
54 | BFO-WorkOrderNotification:v1.0 | WorkOrderNotification | /v1/{capability}/work-order/notifications | BFO
55 | BFO-ZQuote:v1.0 | Zquote | /v1/{capability}/zquotes | BFO
56 | BFS-PartsOrder:v1.0 | PartsOrder | /v1/{capability}/parts-orders | BFO
57 | BFS-ServiceContract:v1.0 | ServiceContract | /v1/{capability}/service-contracts | BFS
58 | Blackline-JournalEntry:v1.0 |  |  | Blackline
59 | CKM-FAQ:v1.0 | FAQ | /v1/{capability}/faq | CKM
60 | CKM-Private-FAQ:v1.0 | PrivateFAQ | /v1/{capability}/private-faq | CKM
61 | CMS-CreditRequest:v1.0 | CreditRequest | /v1/{capability}/credit-requests | CMS
62 | CPQ-Quote:v1.0 |  |  | CPQ
63 | DFSERP-DOMFinanceDocument:v1.0 |  |  | DFSERP
64 | Distributor-SPJ-Rebate:v1.0 |  |  | SPJ
65 | Distributor-SPJ-Rebate:v1.1 |  |  | SPJ
66 | EAA-Case:v1.0 |  |  | EAA
67 | EBILL-Account:v2.2 |  |  | EBILL
68 | EBILL-Account:v2.3 |  |  | EBILL
69 | EBILL-AccountingPeriod:v1.0 | AccountingPeriod | /v1/{capability}/accounting-periods | EBILL
70 | EBILL-Authentication:v1.0 |  |  | EBILL
71 | EBILL-BFO-AccountProfile:v2.0 | AccountProfile | /v2.0/{capability}/account-profiles | EBILL
72 | EBILL-CheckProductEligibility:v1.0 | ProductEligibility | /v1/{capability}/product-eligibility | EBILL
73 | EBILL-Contact:v1.0 |  |  | EBILL
74 | EBILL-GSE-Site:v3.0 |  |  | EBILL
75 | EBILL-Invoice:v2.0 |  |  | EBILL
76 | EBILL-PaymentMethod:v1.1 | PaymentMethod | /v1.1/{capability}/payment-methods | EBILL
77 | EBILL-Staging:v1.0 | Staging | /v1/{capability}/staging | EBILL
78 | EBILL-Staging:v1.1 | Staging | /v1.1/{capability}/staging | EBILL
79 | EBILL-Staging:v2.0 | Staging | /v2/{capability}/staging | EBILL
80 | EBILL-Subscription:v2.4 | Subscription | /v2.4/{capability}/subscriptions | EBILL
81 | EBILL-UpdateAccount:v1.0 |  |  | EBILL
82 | EBILL-Usage:v1.0 | Usage | /v1/{capability}/usage | EBILL
83 | Edicom-Invoice:v1.0 |  |  | Edicom
84 | Email:v1.0 | Email | /v1/{capability}/email | Email
85 | ERP-Client:v1.0 | Client | /v1/{capability}/clients | ERP
86 | ERP-CostCenter:v1.0 | CostCenter | /v1/{capability}/costcenters | ERP
87 | ERP-CostCenter:v1.1 | CostCenter | /v1.1/{capability}/costcenters | ERP
88 | ERP-Employee:v1.0 |  |  | ERP
89 | ERP-HoldSource:v1.0 | HoldSource | /v1/{capability}/holdsources | ERP
90 | ERP-InboundDelivery:v1.0 | InboundDelivery | /v1/{capability}/inbound-deliveries | ERP
91 | ERP-InternalOrder:v1.0 | InternalOrder | /v1/{capability}/internal-orders | ERP
92 | ERP-PostFinanceDocument:v1.0 |  |  | ERP
93 | ERP-Price:v1.0 | Price | /v1/{capability}/price | ERP
94 | ERP-Price:v2.0 | Price | /v2/{capability}/price | ERP
95 | ERP-ProjectOrder:v1.0 | ProjectOrder | /v1/{capability}/projectorders | ERP
96 | ERP-PSProject:v1.0 | PSProject | /v1/{capability}/ps-projects | ERP
97 | ERP-PurchaseOrder:v1.0 | PurchaseOrder | /v1/{capability}/purchase-orders | ERP
98 | ERP-SalesOrder:v1.0 |  |  | ERP
99 | ERP-SalesOrder:v3.1 |  |  | ERP
100 | ERP-SalesOrder:v4.0 |  |  | ERP
101 | ERP-SalesOrderBOM:v1.0 |  |  | ERP
102 | ERP-SalesOrderBOM:v2.0 |  |  | ERP
103 | ERP-ServiceOrder:v1.0 |  |  | ERP
104 | ERP-Stock:v1.0 |  |  | ERP
105 | ERP-TransferOrder:v1.0 | TransferOrder | /v1/{capability}/transferorders | ERP
106 | ERP-TransferOrder:v1.1 | TransferOrder | /v1.1/{capability}/transferorders | ERP
107 | ERP-WBS:v1.0 | WBS | /v1/{capability}/wbs | ERP
108 | EUT-GetVATDetails:v1.0 | VATDetails | /v1/{capability}/vat-details | EUT
109 | FIO-FulfillPayments:v1.0 | PaymentFulfillment | /v1/{capability}/payment-fulfillments | FIO
110 | FIO-FulfillProvisioning:v2.0 | ProvisionFulfillment | /v2/{capability}/provision-fulfillments | FIO
111 | GoDigital-User:v1.0 |  | / | GoDigital
112 | GoDigital-User:v1.1 |  | / | GoDigital
113 | GSE-EntitlementLineItem:v2.0 | EntitlementLineItem | /v2/{capability}/entitlement-line/items | GSE
114 | GSE-EntitlementLineItem:v3.0 | EntitlementLineItem | /v3/{capability}/entitlement-line/items | GSE
115 | GSE-FulfillEntitlements:v2.0 | FulfillEntitlements | /v2/{capability}/fulfill/entitlements | GSE
116 | GSE-TransferEntitlementLineItems:v2.0 | TransferEntitlementLineItem | /v2/{capability}/transfer-entitlement/lineitems | GSE
117 | GSE-User:v2.0 |  | / | GSE
118 | IDMS-Transliteration:v2.0 | Transliteration | /v2/{capability}/transliteration | IDMS
119 | IDMS-User:v3.0 |  |  | IDMS
120 | IDMS-User:v4.1 |  |  | IDMS
121 | IFW-JobManagement:v1.0 | JobManagement | /v1/{capability}/job-management | IFW
122 | IFW-ReferenceIds:v1.0 |  |  | IFW
123 | InstalledBase:v3.0 | InstalledBase | /v3/{capability}/installedbase | InstalledBase
124 | InstalledBase:v3.1 | InstalledBase | /v3.1/{capability}/installedbase | InstalledBase
125 | InstalledBase:v4.0 | InstalledBase | /v4/{capability}/installedbase | InstalledBase
126 | MDG-Supplier:v1.0 |  |  | MDG
127 | MDM-AddressFinder:v1.0 | AddressFinder | /v1/{capability}/address-finder | MDM
128 | MES-Product:v1.0 |  |  | MES
129 | MYSE-Order:v2.0 |  |  | MYSE
130 | MYSE-OrderSummary:v1.0 | OrderSummary | /v1/{capability}/order-summary | MYSE
131 | MYSE-PriceAndAvailability:v2.1 | PriceAndAvailability | /v2.1/{capability}/priceandavailability | MYSE
132 | MySE-ProductAvailability:v2.1 | ProductAvailability | /v2.1/{capability}/product-availability | MySE
133 | MYSE-TempAccountAccess:v1.0 | TempAccountAccess | /v1/{capability}/temp-account/access | MYSE
134 | MYSE-User:v1.0 |  | / | MYSE
135 | Newton-FeatureAcknowledgement:v1.0 | FeatureAcknowledgement | /v1/{capability}/feature-acknowledgements | Newton
136 | Newton-QuoteAcknowledgement:v1.0 | QuoteAcknowledgement | /v1/{capability}/quote-acknowledgements | Newton
137 | Newton-SalesOrderAcknowledgement:v1.0 | SalesOrderAcknowledgement | /v1/{capability}/salesorder-acknowledgement | Newton
138 | Newton-SalesOrderErrorAcknowledgement:v1.0 | SalesOrderErrorAcknowledgement | /v1/{capability}/salesorder-erroracknowledgement | Newton
139 | Newton-SalesOrderPriceAcknowledgement:v1.0 | SalesOrderPriceAcknowledgement | /v1/{capability}/salesorder-price-acknowledgement | Newton
140 | Newton-SPJRebateAcknowledgement:v1.0 | RebateAcknowledgement | /v1/{capability}/rebate-acknowledgements | Newton
141 | Newton-SPJRebateErrorAcknowledgement:v1.0 | RebateErrorAcknowledgement | /v1/{capability}/rebate-error/acknowledgements | Newton
142 | OneTool-Ticket:v1.0 | Ticket | /v1/{capability}/tickets | OneTool
143 | Oracle-SOAP-ERP-SalesOrderServiceContract:v1.0 |  |  | ERP
144 | PIM-Document:v1.0 |  |  | PIM
145 | PIM-File:v1.0 |  |  | PIM
146 | PIM-IncrementalCategory:v1.0 | IncrementalCategory | /v1/{capability}/incremental-categories | PIM
147 | PIM-IncrementalDocument:v1.0 | IncrementalDocument | /v1/{capability}/incremental-documents | PIM
148 | PIM-Product:v1.0 |  | / | PIM
149 | PIM-Product:v1.1 |  | / | PIM
150 | PIM-Product:v2.0 |  | / | PIM
151 | PIM-ProductOffer:v1.0 | ProductOffer | /v1/{capability}/product-offers | PIM
152 | PRM-Cockpit:v1.0 | Cockpit | /v1/{capability}/cockpit | PRM
153 | PRM-Invoice:v1.0 |  | / | PRM
154 | PRM-Notification:v1.1 | Notification | /v1/{capability}/notifications | PRM
155 | PRM-PartnerLocator:v1.0 | PartnerLocator | /v1/{capability}/partner-locator | PRM
156 | PRM-Profile:v1.0 | Profile | /v1/{capability}/profiles | PRM
157 | PRM-Registration:v1.0 | Registration | /v1/{capability}/registration | PRM
158 | Product-Availability:v1.0 | ProductAvailability | /v1/{capability}/productavailability | Product
159 | Product-StockLevelChecker:v1.0 | ProductStockLevel | /v1/{capability}/product-stock/levels | Product
160 | Q2C-Feature:v1.0 | Feature | /v1/{capability}/features | Q2C
161 | Q2C-Quote:v1.0 |  |  | Q2C
162 | Q2C-SPJRebate:v1.0 |  |  | Q2C
163 | SAPERP-JournalEntry:v1.0 |  |  | SAPERP
164 | SAP-Job:v1.0 |  |  | SAP
165 | SDH-Account:v1.0 |  |  | SDH
166 | SDH-Asset:v1.0 |  |  | SDH
167 | SDH-CrossRef:v1.0 | CrossRef | /v1/{capability}/cross-ref | SDH
168 | SDH-CrossRef:v2.0 | CrossRef | /v2/{capability}/cross-ref | SDH
169 | SDH-Employee:v1.0 |  |  | SDH
170 | SDH-EmployeeBulk:v1.0 | EmployeeBulk | /v1/{capability}/employee-bulk | SDH
171 | SDH-Hierarchy:v1.0 | Hierarchy | /v1/{capability}/hierarchy | SDH
172 | SDH-Material:v1.0 | Material | /v1/{capability}/material | SDH
173 | SDH-MultiCurrency:v1.0 | MultiCurrency | /v1/{capability}/multi-currency | SDH
174 | SDH-Search:v1.0 |  |  | SDH
175 | SDH-Search:v2.0 |  |  | SDH
176 | SEACat-Asset:v1.0 |  |  | SEACat
177 | SEACat-User:v1.0 |  |  | SEACat
178 | ServiceChannel-BFS-WorkOrder:v1.0 | WorkOrder | /v1/{capability}/work-orders | BFS
179 | SOAP-BFO-GetCase:v1.0 |  |  | BFO
180 | SOAP-BFO-GetCase:v1.0 |  |  | BFO
181 | SOAP-BFO-GetGateManagers:v1.0 |  |  | BFO
182 | SOAP-BFO-RegisterCase:v1.0 | RegisterCase | /v1/{capability}/register-cases | BFO
183 | SOAP-BFO-UpdateOpportunityQuote:v1.0 | OpportunityQuote | /v1/{capability}/opportunity-quotes | BFO
184 | SOAP-BFO-UpdateOpportunityQuote:v2.0 | OpportunityQuote | /v2/{capability}/opportunity-quotes | BFO
185 | SOAP-EBILL-GetSubscriptionDetails:v1.0 | SubscriptionDetails | /v1/{capability}/subscription-details | EBILL
186 | SOAP-ERP-CreateSalesOrder:v1.0 |  |  | ERP
187 | SOAP-ERP-GetMaterialInventoryDetails:v1.0 | MaterialInventoryDetails | /v1/{capability}/material-inventory/details | ERP
188 | SOAP-ERP-GetSalesOrderPrice:v2.0 |  |  | ERP
189 | SOAP-ERP-UpdatePlannedCostsAndRevenues:v1.0 | PlannedCostsAndRevenue | /v1/{capability}/plannedcostsandrevenue | ERP
190 | SOAP-ETAX-CalculateTax:v1.0 |  |  | ETAX
191 | SOAP-EUT-GetVATDetails:v1.0 | VATDetails | /v1/{capability}/vat-details | EUT
192 | SOAP-FIO-FulfillPayments:v1.0 | SOAPPaymentFulfillment | /v1/{capability}/soap-payment/fulfillments | FIO
193 | SOAP-FIO-FulfillProvisioning:v1.0 | SOAPProvisionFulfillment | /v1/{capability}/soap-provision/fulfillments | FIO
194 | SOAP-GSE-CreateDeviceEntitlement:v1.0 | DeviceEntitlement | /v1/{capability}/device-entitlements | SOAP-GSE
195 | SOAP-GSE-EntitlementOrder:v1.0 | EntitlementOrder | /v1/{capability}/entitlement-orders | SOAP-GSE
196 | SOAP-GSE-EntitlementOrder:v1.1 | EntitlementOrder | /v1.1/{capability}/entitlement-orders | SOAP-GSE
197 | SOAP-GSE-EntitlementOrder:v2.0 | EntitlementOrder | /v2/{capability}/entitlement-orders | SOAP-GSE
198 | SOAP-GSE-ManageDevice:v1.0 | ManageDevice | /v2/{capability}/manage-devices | SOAP-GSE
199 | SOAP-GSE-ProductPackagingService:v1.0 | ProductPackaging | /v1/{capability}/product-packaging | SOAP-GSE
200 | SOAP-GSE-ProductPackagingService:v2.0 | ProductPackaging | /v2/{capability}/product-packaging | SOAP-GSE
201 | SOAP-GSE-UserOrgHierarchy:v1.0 | UserOrgHierarchy | /v1/{capability}/user-org-hierarchy | SOAP-GSE
202 | SOAP-GSE-UserOrgHierarchy:v2.0 | UserOrgHierarchy | /v2/{capability}/user-org-hierarchy | SOAP-GSE
203 | SOAP-GSE-UserOrgHierarchy:v3.0 | UserOrgHierarchy | /v3/{capability}/user-org-hierarchy | SOAP-GSE
204 | SOAP-IFW-CustomerFeedAcknowledgement:v1.0 | CustomerFeedAcknowledgement | /v1/{capability}/customer-feed/acknowledgement | SOAP-IFW
205 | SOAP-ITDERP-CreditApplication:v1.0 | CreditApplication | /v1/{capability}/credit-applications | SOAP-ITDERP
206 | SOAP-LicenseService:v1.0 | LicenseService | /v1/{capability}/license-service | SOAP
207 | SOAP-OneClick-CreateSalesOrderBOM:v1.0 |  |  | SOAP-OneClick
208 | SOAP-OneClick-MaintainSalesOrder:v1.0 |  |  | SOAP-OneClick
209 | SOAP-OneClick-Satelite-UpdatePSProject:v1.0 |  |  | SOAP-OneClick-Satelite
210 | SOAP-OneTool-Ticket:v1.0 | SOAPTicket | /v1/{capability}/soap-tickets | SOAP-OneTool
211 | SOAP-OneTool-TicketOutbound:v1.0 | TicketOutbound | /v1/{capability}/ticket-outbound | SOAP-OneTool
212 | SOAP-PIM-Document:v1.0 |  | / | SOAP-PIM
213 | SOAP-SAPCN-ATPCheck:v1.0 | ATPCheck | /v1/{capability}/atp-check | SOAP-SAPCN
214 | SOAP-SAPCN-OGStockCheck:v1.0 |  | / | SOAP-SAPCN
215 | SOAP-SDH-ApplyMultiCurrency:v1.0 | SOAPMultiCurrency | /v1/{capability}/soap-multi-currency | SOAP-SDH
216 | SOAP-SDH-GetAccount:v1.0 |  | / | SOAP-SDH
217 | SOAP-SDH-GetCrossReference:v1.0 | SOAPCrossReference | /v1/{capability}/soap-cross-references | SDH
218 | SR-Auth:v1.0 |  | / | SR
219 | SR-BOM:v1.0 |  | / | SR
220 | SR-Bookmark:v1.0 | Bookmark | /v1/{capability}/bookmarks | SR
221 | SR-Community:v1.0 | Community | /v1/{capability}/community | SR
222 | SR-Document:v1.0 |  | / | SR
223 | SR-Preference:v1.0 | Preference | /v1/{capability}/preference | SR
224 | SR-Product:v1.1 |  | / | SR
225 | SR-Repository:v1.2 | Repository | /v1.2/{capability}/repository | SR
226 | SR-SharedCommunity:v1.1 | SharedCommunity | /v1/{capability}/shared-community | SR
227 | SR-Switchboard:v1.1 | Switchboard | /v1.1/{capability}/switchboard | SR
228 | SR-User:v1.0 |  |  | SR
229 | SSPSRM-Supplier:v1.0 |  |  | SSPSRM
230 | SXON-Case:v1.0 |  |  | SXON
231 | TalentLink-BulkEmployee:v1.0 |  |  | TalentLink
232 | TalentLink-BulkEmployee:v2.0 |  |  | TalentLink
233 | TalentLink-Employee:v1.0 |  |  | TalentLink
234 | TalentLink-Employee:v2.0 |  |  | TalentLink
235 | UIMS-User:v2.0 |  |  | UIMS