## Delivery Task Checklist (hidden)
API - Delivery - Build Sub Task
Validate the API specification
Validate and understand the APIM requirements - Complete any gaps- ADR-2 session if required
Clarify project milestones with PM - Provide status updates for PM
Create API spec in GIT and on the portal - Compose slogan line for the portal tile
Develop Proxy in edge UI
Consider appropriate reuse, refactoring or creation of common Shared Flows
Unit test - Write postman scripts - Get real test data from project team
Connectivity test if the backend is new or going through the reverse proxy
Prepare connectivity guide for consumers - Highlight where behavior differs from the API spec
API - Delivery - Test Support Sub Task
Participate in SIT troubleshooting session(s) - Debug errors collaboratively
Update code to map native backend errors to standard error responses
UAT support - Educate consumer and backend developers
Fix any APIM defects reported during UAT
Check in Proxy and configuration scripts for 7 environments to GIT
Check in unit test collection to GIT
Update APIM requirement doc and API spec if any detail changed - Refresh spec on the portal
Update API name in the demand pipeline file
[Support API Certification Assessment for some APIs]
API Delivery - Deployment - Sub Task
Prepare deployment guide for Production/Pre-Prod release
Upload docset to Box - Requirement doc, Connectivity guide, Deployment Guide, [Mapping File]
Check in Prod/Pre-prod configuration delta scripts to GIT Release branch
Ensure final version of proxy, shared flows, and configs are checked into GIT
Propagate merged GIT master to environment branches before CCB
Enter move request into CCB list - Attend CCB
Attend code promotion work session and smoke test on Preprod/Prod (Sandbox)
[Share production credentials with the platform owner if a new app is registered]
[Hypercare daily meeting and troubleshooting for 2 weeks, requested for some APIs]
Compose API business value statement and post to the Teams channel
API - Delivery Team - Daily Tasks
Review GIT Pull Requests for other delivery team members
Update daily scrum and delivery backlog in Notebook
Handle project-related communication (email queries, chats, opt-out explanations)
Read teams channel and yammer postings
API - Delivery Team - Weekly Tasks
API Design Review & APIM requirements capture - Attend 2-3 per week
Attend weekly team meeting
Attend weekly knowledge share meeting
Update weekly achievements page on Friday
Reserve % Capacity for other Tasks (non-Delivery) | Effort is variable and adds up to a lot of time => impacts delivery bandwidth
Refer stakeholders with general queries to process links/meetings
Production support spillover
Platform workstream spillover
Migration workstream spillover
"Smile program" assignment - collaboration in pairs on particular topic

## SOD-DEV
PRE-DELIVERY-STEPS-CLOSURE | CHECK LIST | STATUS
ADR Review | API specification is reviewd as per APIM guidelines . All the design and refactoring options are discussed and closed. | Done
| APIM requirment document is updated and uploaded to BOX | Done
DEV - CLOSURE
DEV Task | Verify Spec is valid | Done
| Validate APIM requirment document has all the information for devlopment-Set up ADR-2 if required | Done
| Create spec in spec store with minor version naming | Done
| Create new proxy from the template proxy with major version naming | Done
| Update and implement proxy as per the spec and APIM requirment | Done
| Create config - Try to reuse KVM . Justification required to create new KVM | Done
| Create Target Sever - Try to reuse if not present create new | Done
| Deploy the proxy and config into only DEV | Done
| Write unit test using postman and test - Test case should pass 100% | Done
| Create a branch from master with demand name and check in the code to branch | Done
| Send PR to master for code review | Done
| Once the code is approved and merged send a request to deploy it in QA | Done
| Prepare connectivity guide with required details for application team to do UAT | Done
DEV - STATUS |  | Completed

## SOD-QA
PRE-QA-STEPS-CLOSURE | CHECK LIST | STATUS
DEV-STATUS | Dev Status should be completed | Done
QA-CLOSURE
INTERNAL QA | Review the Implementation with APIM requirment | Done
| Execute the test cases and validate all the test are success | Done
QA SIGN OFF |  | Success

## SOD-UAT
PRE-UAT-STEPS-CLOUSER | CHECK LIST | STATUS
QA-SIGN OFF | QA Sign off should be success | Done
UAT-CLOSURE
UAT TASK | Initate UAT request with project team | Done
| Share the Conectivity guide | Done
| Resolve any issue identified duting UAT | Done
| Get UAT sign off from the project team team | Done
UAT-SIGN OFF |  | Success

## SOD-PPR
PRE-PPR-STEPS-CLOUSER | CHECK LIST | STATUS
UAT SIGN OFF | UAT Sign off should be success | Done
PPR CLOUSER
Task | Prepare config for pre-prod | Done
| Checkin and merge pre-prod config | Done
| Prepare Deployment guide | Done
| Add entry to CRB | Done
| Support and validate during deployment | Done
PRE -PROD -STATUS |  | Completed

## SOD-PR
PRE-PR-STEPS-CLOUSER | CHECK LIST | STATUS
PRE -PROD -STATUS | Status should be Completed | Done
PR CLOUSER
Task | Prepare config for prod | Done
| Checkin and merge prod config | Done
| Prepare Deployment guide | Done
| Add entry to CRB | Done
| Support and validate during deployment | Done
| Warranty Support | Started
PROD -STATUS |  | Completed